## Sheet1
CHB_7011 |  | Horseshoe Lane Chadlington - New House
Section | Item | Description
1 | Lower Foundations
| 1.01 | Mark out Sub-Slab Foundations
| 1.02 | Excavate to Foundations to Depths Shown on Drawings
| 1.03 | Identify and Locally Replace any Soft Spots with Granular Material
| 1.04 | Building Control / Approving Authority to Inspect Agree Formation Levels and Safe Ground Bearing Pressure. Excavate Foundations to agreed Formation if deeper
| 1.05 | Cast Mass Concrete to Footings to Levels Shown on Drawings
2 | Groundslab
| 2.01 | Import Hardcore
| 2.02 | Undertake Test Rolling to Establish Amount of Potential Material Loss into Clay, if any
| 2.03 | Examine Prepared Slab Formation Level for Soft Spots.Remove and Replace with Granular Material Locally
| 2.04 | Lay Terram if Deemed Necessary by Initial Test
| 2.05 | Spread Hardcore and Roll in Layers to Specified Depth and Profile as Drawings
| 2.06 | Concrete Blind Completed Hardcore to Profiles as Drawings (Consider Blinding Slope Below Front of Cottage at this Stage to Protect)
| 2.07 | Lay Specified PE Slip Membrane
| 2.08 | Provide Shutters to Slab Edges to Lines and Profiles
| 2.09 | Fix Lower Loose Bar Reinforcement to Edge Profiles and Step Details Use Spacers to Maintain Specified Covers
| 2.1 | Accurately Position Projecting Starter Bars for Hollow Block Retaining Walls
| 2.11 | Lay Bottom Mesh on Spacers, Place Internal Spacers and Lay Top Mesh
| 2.12 | Cast Specified Concrete
| 2.13 | Finish Surface to Required Standard
| 2.14 | Strip Side Shutters
| 2.15 | Lay Specified Waterproof DPM to Specialist Details. Seal to Projecting Reinforcement for Retaining Walls
3 | Retaining Walls
| 3.01 | Prepare and Lay First Row of 215 Hollow Core Blocks - Arrangement is Indicated on the Drawings
| 3.02 | Construct the Retaining Walls to Levels and Profiles Detailed. Ensure the Cores are Kept Free and Clear of Mortar Snots Ensure No Debris Collects at Bottom of Cores Keep Faces Clean of Mortar as Work Proceeds Build In Wall Ties for the Inner Leaf as Work Proceeds
| 3.03 | Install Single Vertical Bar to Each Core Lapping with Starter Bar at Bottom of Cores and accurately Locate Mid-Width in the Core
| 3.04 | Place Infill Concrete and Vibrate
| 3.05 | Apply Specified Tanking Membrane to Specialist Details
| 3.06 | Provide Suitable Protection Board as Necessary
| 3.07 | Lay Pea Gravel Pipe Bedding at Slab Edges to Base Retaining Walls
| 3.08 | Lay Collection Pipe System with Tails Beyond the Rear Line of the House
| 3.09 | Cover with Pea Gravel
| 3.1 | Backfill Side Retaining Walls in Stages with Free-Draining Granular Fill (Alternative - Use Proprietary Drainage Sheet and Backfill with Well Graded Material). Suitably Compacted as Filling Proceeds.
4 | Upper Foundations
| 4.01 | Foundations
| 4.02 | Excavate to Foundations to Depths Shown on Drawings
| 4.03 | Identify and Locally Replace any Soft Spots with Granular Material
| 4.04 | Building Control / Approving Authority to Inspect Agree Formation Levels and Safe Ground Bearing Pressure. Excavate Foundations to agreed Formation if deeper
| 4.05 | Cast Mass Concrete to Footings to Levels Shown on Drawings
| 4.06 | Place Lintels to Support Dividing Walls to Front Projection
| 4.07 | Place Supports to Side Walls to Span Gap From Deep Side Foundation and Retaining Wall (Site Dimension Required for Design)
| 4.08 | Concrete Blind Void Under Suspended Floor
5 | Masonry to Lower Storey
| 5.01 | Raise Inner Leaf Blockwork, with Cavity Insulation and Starter Bond Blocks for Internal Walls , to profile of Retaining Walls
| 5.02 | Prepare for DPM Details
| 5.03 | Raise Full Insulated Cavity Wall Construction above Side Retaining Walls including Starter Bond Blocks for Internal Walls and Building-In DPCs and Window Lintels
| 5.04 | Raise Internal Loadbearing Walls, Bonded to Side Walls, to Required Levels including Lintels and Trimmer Beams
| 5.06 | Temporarily Prop all Lintels and Trimmers
| 5.07 | Provide Propping System Paralell to Rear Wall and Inset to Inner Leaf (Enables Casting of Insitu Edge/Lintel Detail Monolithic with Floor Units)
| 5.08 | Provide Shuttering to Openings in Rear Wall (Propping Required)
| 5.09 | Fix Reinforcement as Detailed to Continuous Insitu Floor Edge Detail
6 | Beam and Block Floors
| 6.01 | Install Proprietary Beams to Rear Span (Terrace) Note: Far End will be Bearing on Props at this Stage
| 6.02 | Lay Infill Blocks. Not in Zones Paralell/Local to Rear Wall or Edge Make-Up or Light Tube Width
| 6.03 | Shutter for Light Tube and Position Mesh
| 6.04 | Shutter Side Strips to Full Beam Depth, Position Upstand Reinforcement to Side Parapet Walls and Cast
| 6.05 | Cast Concrete to Rear Wall Downstand, Edge Make-Ups and Light Tube Bay
| 6.06 | Slurry Concrete to General Block Infill Areas to Complete
| 6.07 | Build Up Support Wall to Line of Upper Rear Wall
| 6.08 | Build up Upper Rear Wall Outer Leaf to Sill Level of Openings
| 6.09 | Affix GMS Restraint Straps to Side Walls
| 6.1 | Provide Bonding Agent to Deck Area
| 6.12 | Lay Anti-Crack Mesh to Terrace Area
| 6.13 | Cast Concrete to Falls as Detailed
| 6.14 | Install Ventilation to Underslab Void to Front Floor Spans
| 6.15 | Install Proprietary Beams to Remainder of Upper Ground Floor
| 6.16 | Lay Infill Blocks
| 6.17 | Slurry Concrete to General Block Infill Areas to Complete
| 6.18 | Affix GMS Restraint Straps to Side Walls
7 | Cottage | (Traditional Construction)
| 7.01 | Raise Walls of Cottage to Rear Single Storey Ceiling Level
| 7.02 | Build 450mm Wall Height with 3 Levels of Bed Joint Ladder Reinforcement Across Gables (Tied Ladders)
| 7.03 | Build-In Padstones and Leave Pockets for Beams to Rear Low Level Roof
| 7.04 | Raise Walls to Cottage Eaves and Gable Profiles. Include Cavity Trays
| 7.05 | Erect Main Roof Trusses (Design by Specialist Supplier)
| 7.06 | Complete Timber Roof Framing
| 7.07 | Affix GMS Restraint Straps to Gable/Side Walls
| 7.08 | Batten & Tile Roofs
8 | Rear | (Traditional Construction)
| 8.01 | Raise Rear Wall to Underside of Openings
| 8.02 | Raise Side Walls to Profile on Drawings (Different Each Side)
| 8.03 | Provide Shuttering to Capping Beam to Rear Wall. Propping Required to Openings
| 8.04 | Fix Reinforcement, as Detailed, to Continuous Insitu Curved Beam Detail
| 8.05 | Include Cast-In Fixings for Outer Leaf Support Angle over Openings
| 8.06 | Install 4nr. Steel Beams Supported by Rear Beam to Inner Leaf and Cottage
| 8.07 | Fix Timber Wall Plate to Inner Leaf Line Binder
| 8.08 | Fix Timber Grounds (2 levels) to Rear Wall of Cottage
| 8.09 | Install Ceiling Joists
| 8.1 | Position Rafters (Slopes Vary) and Cut Vertical Support to Each Member Bearing onto the Binders. Complete Propping with Head Ties and Diagonals.
| 8.11 | Provide Noggins to Full Prop Line
| 8.12 | Affix GMS Restraint Straps to Side Walls
| 8.13 | Affix Outer Leaf Support Angles over Openings and Raise Outer Leaf to Level
| 8.14 | Ply Sheath the Roof and Prepare for Specialist Zinc Weathering
| 8.15 | Prepare Overhang of Rafters at Eaves for Secret Gutter Detail
9 | Main Stairs
| 9.01 | Construct Liner Wall to Profile of Underside of Stair inside Loadbearing Corridor Walls
| 9.02 | Construct Insitu Concrete Stair Spanning onto Side Walls. Top Section over Walk-Through to Span from Closing Wall to Retaining Wall Inner Leaf.
10 | Rear Guarding to Periphery of Terrace
| 10.01 | Proprietary Guarding to Curved Rear Wall - TBA
| 10.02 | Reinforced Masonry Guarding to Sides - TBA
11 | Internal Fit-Out
| 11.01 | To Schedule by Others
12 | External Finishes
| 12.01 | To Schedule by Others
13 | External Landscaping
| 13.01 | To Schedule by Others